## Slide 1: DDWG Update
Steve Hughes
MC Face-to-Face
UMD, College Park, MD
March 27-28, 2012

## Slide 2: Topics
Summary of Progress to Date
RFA Status
Plans for Build 2c
Next Steps

## Slide 3: Summary of Progress to Date
  Released PDS4 Data Standards V0.600h for Build 2b on January 31
  Updated product label preamble
  Updated Table classes
    required for LADEE/MAVEN data products
  Implemented XML Schema 1.1 capabilities.
  Created a Data Provider Wiki with FAQ.
  Provided “catalog” products for testing.
  All DDWG Build 2b RFAs have been delivered/ implemented.

## Slide 4: Summary of Progress to Date
  Development since Build 2b
    Good progress in learning how to use “master” schemas
    Updated Array class
      Required for LADEE data product
    Added Packed_Data_Fields for bit fields to Table_Binary
    Simplified Product_Collection, Product_Context, and Product_SPICE_Kernel.
    Using new validation mechanism for XML product labels.
      Schematron is a rule-based validation language for making assertions.
    Started adding meanings to the data dictionary “value meaning” section.
      For example, in filter_name = T15, what does T15 mean?
    An incremental version is planned to support testing.

## Slide 5: RFA Summary
Build 2b
  The majority of the RFAs were DELIVERED by implementing the recommendations that resulted from the special teams process.
    Review/recommend team; recommendations review team; implementation team
    Special topics: e.g. label preamble, table, array, bundle collection, schematron
  The PDS4 data standards were delivered for LADEE & MAVEN product development as scheduled on Jan 31st
    The DDWG continues to support the lead nodes as needed.
Build 2c
  Most of the pending RFAs are documentation related; The goal for Build 2c is a significant update of PDS4 Data Standards documentation.

## Slide 6: DDWG RFA Status
  Pending – 10 Documentation
  - 3 Local Data Dictionary
  - 1 RS Data Formats
  - 1 Data Structure Issues
  Follow-up - 1 Magic Number
Build 2b
  OPEN 0
  PENDING 0
  DELIVERED 26
  CLOSED 3
  TOTAL 29
Build 2c
  OPEN 0
  REQUIRES FOLLOW-UP 1
  PENDING 15
  IMPLEMENTED 22
  CLOSED 5
  TOTAL 33

## Slide 7: Plans for Build 2c
Documentation, Documentation, Documentation
  Information Model being updated and deployed for online access to class, attribute, value, and term definitions.
  More details to follow.
Comprehensive testing of the core model is required.
  Includes node testing of the products and data objects, from binary tables to bundles and collections.
  Includes continued development and testing of the validation rules in the schematron files.
  Identify missing discipline classes.
Significant updates to the schematron files are planned.

## Slide 8: Next Steps
Obtain MC support for node testing of the core model.
Freeze an incremental release of the schemas and information model for testing.
Test the core model.
  Address the issues found.
  Update the schematron files as necessary.
  Identify missing discipline classes.
Deliver a updated suite of the data standards documentation.
Release a new version of the data standards and documentation for build 2c by May 31.

## Slide 9: Liens
Build 2c – Spice Products
  Due to upcoming SPICE class (mid April) and large amount of work on the new toolkit release (planned for the end of April) NAIF will not be able to participate in this test.
  NAIF will need to test the SPICE part of the model as part of 2d activities.

## Slide 10: Questions and Answers

## Slide 11: Backup

## Slide 12: Build 2b Scope
Begin PDS4 label design for LADEE and MAVEN; Begin planning/testing migration (post release)
Deploy a PDS4 standard that supports the Policy on “Acceptable PDS4 Data Formats”
Transition the central catalog to the registry infrastructure
Deploy early PDS4 software tools and services

## Slide 13: Summary of Progress to Date
Key DDWG Liens Areas from ORR
  Information Model
    Compiled, reviewed, and applied a list of high priority actionable items.
    54 action items completed to date.
  Local Data Dictionary (LDD)
    Documented the then current local data dictionary process in a wiki and generated local schema and DD reports for LADEE and MAVEN
    Have since proposed a new LDD approach.
  PDS4 Data Standards Documentation
    Made minimal changes to current documentation.
    Created a Wiki site for new information.
  PDS4 Master Schema (aka Extension Schema)
    Implemented XML Schema 1.1, made related changes, and delivered schemas on schedule.

## Slide 14: PDS4 Documents and their Relationships
Concepts
Document
Big Picture
Standards
Reference
Requirements
User Friendly
XML Schemas
Blueprints
PDS4
Product Labels
Deliverables
Data Dictionary
Definitions
PDS4 Information
Model Specification
Requirements
Engineering Specification
Data Dictionary
Tutorial
Informative
Data Provider’s
Handbook
Cookbook
derive
generate
references
create /
validate
instruct
generate
references
Registry
Configuration File
Object Descriptions
configure
generate
Registry
Product Tracking and Cataloging
generate
Informative
Document
Standards
Document
File
System
Legend