## Slide 1
PDS4 Project Report
PDS MC F2F
University of Maryland
Dan Crichton
March 27, 2012

## Slide 2: Agenda
Project Update
DDWG Update and Special Topics
LADEE and MAVEN Update
Data Migration
SDWG
Phasing Plan (beyond build 3)
Marketing

## Slide 3: Summary of Progress to Date
Requirements in place (approved by MC 3/2010)
PDS-wide Architecture defined
Major reviews conducted
Prototype PDS products defined using maturing PDS4 specification
  LADEE team developing labels
  Preparing for MAVEN use of PDS4
6 system builds completed: build 1a, 1b, 1c, 1d, 2a, 2b
Initial transition to PDS4 in place at EN
  Registry and Harvest infrastructure in place at EN
  Central catalog migrated to registry; High level search migrated
  Information model released for limited use.
Extensions now occurring for build 2c
IPDA review of build 2b underway

## Slide 4: Project Lifecycle
Project
Lifecycle
Pre-
Formulation
Formulation
Implementation
Project
Lifecycle
Gates &
Major
Events
Project
Reviews
PDSMC
Concept
Review
(Dec 2007)
Study/
Concepts
Project Plan
PDS4 Prelim
Architecture
PDSMC
Impl
Review
(July 2008)
PDSMC
Preliminary
Design
(August 2009)
PDSMC
Arch
Review
(Nov 2008)
Build 1b Internal Stds Assessment
(Dec 2010)
PDS System
Review
(Mar 2010)
Build 1c
IPDA Stds Assessment
(April 2011)
PDS System Review II
(June 2011)
Build 1d External Stds Assessment
(Aug 2011)
Operational Readiness Review
(November 2011)
PDS4 Design
Begin
Study
Project
Build 1: Prototype
Build 2:
Production
Build 3
1a
1b
1c
1d
KDP: Study
KDP: Prelim Design
KDP: Project
Plan & Arch

## Slide 5: Key Design Decisions & Recommendation from Aug 2009
Replace PDS3 ad hoc information model with a PDS4 information model that is now managed in modern tools (DDWG) (delivered in build 2)
Replace ad hoc PDS3 product definitions with PDS4 products that are defined in the model (DDWG) (delivered in build 2)
Require data product formats to be derivations from a core set; Support transformation from the core set (DDWG) (delivered in build 2)
Replace “homegrown” PDS data dictionary structure with an international standard (ISO 11179 RIM) (DDWG) (delivered in build 2)
Adopt a modern data language/grammar (XML) where possible for all tool implementations (SDWG) (delivered in build 2)
Adopt system of registries to support improved tracking and access (SDWG) (delivered in build 2)
Support remote access to data and services to bring the federation together both for ingestion and distribution (SDWG) (planned for 3)

## Slide 6: What’s been delivered for build 2a and 2b*
Software System
Registry Service
Harvest Tool
Validate Tool
Security Service
Report Service
Search Service
CI Tool
Data Standards
Information Model
XML Schemas
Data Dictionary
Standards Documents**
* PDS4 is following an iterative development model so additional phases will deliver additional capability.
** Documents between build 2a and build2b were not substantially revised

## Slide 7: Build 2b Scope (Delivered)
Begin PDS4 label design for LADEE and MAVEN; Begin planning/testing migration
Deploy a PDS4 standard that supports the Policy on “Acceptable PDS4 Data Formats”
Transition the central catalog to the registry infrastructure
Deploy early PDS4 software tools and services

## Slide 8: RFA Process/Status
RFAs have been captured from reviews
  They are addressed and scheduled for implementation and deployment as part of the build/release process
  Additional RFAs will be captured as part of testing in preparation for build 2c delivery
RFA categorization
  OPEN, ACCEPTED, REQUIRES FOLLOW-UP, PENDING, IMPLEMENTED, DELIVERED, CLOSED, REJECTED
RFA spreadsheet posted at:
  http://pds-engineering.jpl.nasa.gov/pds2010/build2bdeliverables/PDS4-RFA-LIST20120323.pdf

## Slide 9: Major RFA Areas
Information model/standards/schema
  Many addressed for build 2c
Documentation
  Deferred to build 2c
Marketing
  Deferred to build 2c

## Slide 10: RFA Status (Build 2b)
SUMMARY
OPEN 0
PENDING 3
DELIVERED 28
CLOSED 3
Total 34

## Slide 11: RFA Status (Build 2c)
SUMMARY
OPEN 0
REQUIRES FOLLOW-UP 2
ACCEPTED 1
PENDING 20
IMPLEMENTED 31
CLOSED 5
TOTAL 59

## Slide 12: Build 2c Scope (Proposed)
Principal documents including the Standards Reference, Data Providers Handbook, and Concepts Document ready to be posted for public access. (NOTE: Documents may still have some TBD sections for more advanced aspects of PDS4).
Support for additional data products including those with images and bit fields.
Node testing of information model complete for build 2c DDWG test cases.
Resolution of any major MAVEN and LADEE issues.
Central catalog migrated to PDS4 infrastructure.
Registry software ready for distribution to the nodes.

## Slide 13: Build 2c Focus Items
Documentation
  A follow up report from DDWG on this will be given
PDS-wide Testing of IM
  This is important to identify major showstoppers and ensure the delivered RFAs can be closed
  More to come on this
Testing registry software @ EN in production state
Prepare deployment of software across PDS
  PDS-wide registration of data to the product level

## Slide 14: Phasing/Planning
PDS4 is maturing enough that we need to consider how we now build on PDS4
  Mapping to internal development (e.g., upgrade PDS web applications)
  Mapping to upcoming missions
Note that we have not mapped this to either mission forcing functions or any internal ones (e.g., migration)
To be discussed this afternoon

## Slide 15: Build Phasing
Phase | Purpose | Release | Date
I Prototype Build 1 | Release a prototype Ingest Subsystem Baseline PDS4 model, standards reference (beta release) Support testing of Node interfaces Support PDS4 product prototypes | PDS4 beta info model, standards reference, data dictionary, schemas baseline Beta release of Harvest, Registry, Report and Security services First set of process, documentation and tutorial | October 2010
II Operational Build 2 | Initial operational PDS4 system and PDS4 Standards Allow acceptance of PDS4 data into operational archive Support LADEE, MAVEN and Migration Planning Allow user to search and access to both PDS3 and PDS4 data | PDS4 beta info model, standards reference, data dictionary, schemas baseline Production release of Harvest, Registry, Report and Security services Validation and catalog ingest tools Updated documentation Transition from PDS3 catalog to PDS4 registry | January 2012
III Operational Build 3 User Services Capabilities | Incremental release of operational PDS4 system Support data transformation Support science services PDS-wide deployment of PDS4 software | Registry, Harvest deployed at nodes Initial PDS4 library software and transformation support Search protocol deployed | August 2012
IV Web/ Application Integration | Integrated PDS-wide Web Applications with PDS4 Updated look-n-feel for PDS4 | Search protocol integrated into web applications New PDS4 web infrastructure deployed Sharing of data/services among nodes and IPDA | April 2013

## Slide 16: Summary
Good progress on PDS4
Need to now work on preparing PDS4 for wider use
  Testing of the standards is a major need now…
Need to plan development activities to build on top of PDS4
Need to ensuring we map PDS4 schedule to key drivers (e.g., missions, migration, etc)

## Slide 17: Backup

## Slide 18: Schedule