## Slide 1: Build 2c Scope
Principal documents including the Standards Reference, Data Providers Handbook, and Concepts Document ready to be posted for public access. (NOTE: Documents may still have some TBD sections for more advanced aspects of PDS4).
Support for additional data products including images and bit fields.
Node testing of information model complete for build 2c DDWG test cases.
Resolution of any major MAVEN and LADEE issues.
Central catalog migrated to PDS4 infrastructure.
Registry software ready for distribution to the nodes.

## Slide 2: Build Phasing
Phase | Purpose | Release | Date
I Prototype Build 1 | Release a prototype Ingest Subsystem Baseline PDS4 model, standards reference (beta release) Support testing of Node interfaces Support PDS4 product prototypes | PDS4 beta info model, standards reference, data dictionary, schemas baseline Beta release of Harvest, Registry, Report and Security services First set of process, documentation and tutorial | October 2010
II Operational Build 2 | Initial operational PDS4 system and PDS4 Standards Allow acceptance of PDS4 data into operational archive Support LADEE, MAVEN and Migration Planning Allow user to search and access to both PDS3 and PDS4 data | PDS4 beta info model, standards reference, data dictionary, schemas baseline Production release of Harvest, Registry, Report and Security services Validation and catalog ingest tools Updated documentation Transition from PDS3 catalog to PDS4 registry | January 2012
III Operational Build 3 User Services Capabilities | Incremental release of operational PDS4 system Support data transformation Support science services PDS-wide deployment of PDS4 software | Registry, Harvest deployed at nodes Initial PDS4 library software and transformation support Search protocol deployed | August 2012
IV Web/ Application Integration | Integrated PDS-wide Web Applications with PDS4 Updated look-n-feel for PDS4 | Search protocol integrated into web applications New PDS4 web infrastructure deployed Sharing of data/services among nodes and IPDA | April 2013

## Slide 3: DDWG Testing
PDS4 is at a point where PDS-wide testing is critical
The purpose of the test is to validate the information model including:
  Various science data products
  Bundles, Collections
  Documents
  Data dictionaries (global and local)
  Along with the process for generating PDS4 labels

## Slide 4: Build2c Testing
Aspects of the IM will be assigned to nodes by the DDWG
Two-phased approached to be completed by end of May 2012
Phase 1: test simple data products
  PDS3 identified data products
Phase 2: test advanced aspects of PDS4
  Collections, bundles, documents, etc.